## Cover Page
Project_Deliverables_Standards_Checklist Version V1.0 Date: Created by Valampuri NBCUniversal Internal
New Projects | Operations & Technology (O&T)
Enhancements | If we have already developed this and the tabs are already filled, just create a checkpoints only document
Major Enhancements/Adding new Subject areas | Please make sure to fill in all the Tabs or re-use as we might not have all the information

## NBCU Standards
SL No | Best Practices | URL's
1 | Informatica | https://www.dropbox.com/sh/c1lmm5coxz7b90y/AADxuhKzVtp_xJeSAm5OEIo3a?dl=0
3 | Teradata | https://www.dropbox.com/sh/c1lmm5coxz7b90y/AADxuhKzVtp_xJeSAm5OEIo3a?dl=0
4 | Unix Scripts | https://www.dropbox.com/sh/u2gynekmn89rcgr/AAB9-zRCm0LSLDb5DEK9ejvEa?dl=0
5 | CTRL-M | https://www.dropbox.com/sh/o6hel37q9l8w2pb/AAAGkN4MVlSoZAl2ins_pe4Da?dl=0
6 | Data Model | https://www.dropbox.com/sh/8pn613n0jf5jb2h/AAAIia27CCOZJWu4Ps_7OC3Xa?dl=0

## Project Checklist
Project Name : O&T
Non Editable Fields |  |  | Editable fields
Phase | Task Details | Deliverables | Comments | Document Availability(Y/N) | Document Path | Project Comments
Project Grooming | Requirements Gathering | Business Requirements Document,Requirement traceability matrix
| Estimation | Estimation Sheet
| Kick Off Meeting | Project Charter & Milestones
| Project Planning | Project Plan
Solutioning & Discovery | Data Analysis & profiling | Impact Analysis Document,Query Tracker
| Data Modeling | Data model review checklist
| Architecture Design | High level Design Document
| ETL Design | Low Level Design Document
Development | Database Changes | DB scripts
| ETL Mapping Changes | Code / ETL Mapping,ETL Development tracker,Query Tracker
| Unix Script Changes | Shell Scripts
| Unit Testing | Unit Test results, Defect Tracker
QA | Migration & Test Environment Preparation
| Testing & Defect Fixing | QA test plan, QA Test Case results, Defect Tracker, Load Statistics
| UAT testing and support | UAT test Case results, Defect Tracker
Review & Release | Deployment | Deployment Document,Release/Change request
| Post Production Support | Support Documentation,KT handover checklist
| Automation of Data loads | Control-m Job Document
| Release Communications | Communication template

## Governance Track
Integration Governance
S.No | Deployment Date | CR/RITM Number | Change Desc | Checkpoint 1 | Check point 2 | Check point 3 | Check point 4
1
2 | [7 empty] | Check Point 1 | Business Requirement Document Impact Analysis Document Requirement Traceability Matrix High level Design document
3
[8 empty] | Check Point 2 | Low Level Design Document Unit Test Plan & Test Cases Code / Scripts/ SQL Queries Test Results Query Tracker
[8 empty] | Check Point 3 | Stage & UAT Testing Results Defect tracker UAT Sign off Deployment Document Control-m Document
[8 empty] | Check Point 4 | KT Hand Over CheckList/Post Prod Validation
Notes
Define Migration activity window (Monday, Wednesday & Friday)
Production migration window occurs Monday through Thursday (excluding company holidays). All Prod Change tasks are required to be submitted a minimum of a 48 working hours (excludes weekend and company recognized holidays) prior to the requested implementation date/time

## Checkpoint 1
SI No. | Checkpoint RITM# | Checkpoint for | Review Date | Review Comments | Project Team Comments | Status | Final Comments
1
Note on C1: Project/Enhancement Requirement

## Checkpoint 2
SI No. | Checkpoint RITM# | Checkpoint for | Review Date | Review Comments | Project Team Comments | Status | Final Comments
1
2
3
Note on C1: Project/Enhancement Requirement

## Checkpoint 3
SI No. | Checkpoint RITM# | Checkpoint for | Review Date | Review Comments | Project Team Comments | Status | Final Comments
1
Note on C1: Project/Enhancement Requirement

## Checkpoint 4
SI No. | Checkpoint RITM# | CR# | Checkpoint for | Review Date | Review Comments | Project Team Comments | Status | Final Comments
1 | RITM1111111 | CHG0111111 | Project/Enhancement Name Name | Jul-23-2018
Note on D1: Project/Enhancement Requirement