## Estimates
StudioPost Data Integration to Teradata (RITM1475200)
Enhancement / Defect - Effort Estimation | [9 empty] | 10%
Team | System | Module | Tasks | Complexity | Analysis | DEV | QA | UAT | PROD | Buffer | Total (Hrs)
Database | O&T Dashboard | Studio Post | Develop Logical and Physical Design and create 28 new tables (15 Stage + 10 DIM + 3 Fact + 1 static lookup = 29 tables) | L | 3 | 22 | 1 |  | 1 | 2.7 | 29.7
ETL | O&T Dashboard | RCO-Studio Post | Requirements analysis on 16 new tables | L | 4 |  |  |  |  | 0.4 | 4.4
|  |  | Review database model with DBA | L | 2 |  |  |  |  | 0.2 | 2.2
|  |  | Documentation (HLD, LLD and Support documents) | L | 4 |  |  |  |  | 0.4 | 4.4
ETL Development
|  |  | Create 24 new Mappings, 24 new Sessions and 6 Workflows(54 INFA objects) for 24 new tables (15 Stage + 9 DIM = 24 tables) | L |  | 24 |  |  |  | 2.4 | 26.4
|  |  | Capture incremental changes: Create 4 new Mappings, 4 new Sessions and 1 Workflows(9 INFA objects) for 4 new tables (3 DIM + 1 Fact = 4 tables) | M |  | 32 |  |  |  | 3.2 | 35.2
|  |  | Load Lookup tables: Create 7 new mappings, 7 new sessions and 1 workflow( 15 INFA objects) to load 1 lookup tables | L |  | 4 |  |  |  | 0.4 | 4.4
|  |  | Create 3 Wrapper Scripts to invoke 6 workflows | L |  | 3 |  |  |  | 0.3 | 3.3
|  |  | Unit test plan and execution for scripts to load 29 new tables (15 Stage + 10 DIM + 3 Fact + 1 static = 29 tables) | L |  | 10 |  |  |  | 1 | 11
|  |  | Stage deployment requests & migration | L |  |  | 2 |  |  | 0 | 2
|  |  | QA/Stage test plan & execution | L |  |  | 7 |  |  | 0 | 7
|  |  | Production deployment requests and migration | L |  |  |  |  | 3 | 0 | 3
|  |  | Production schedule automation (Control-M job script) | L |  |  |  |  | 2 | 0 | 2
Tableau
.NET
QA
TOTAL Efforts |  |  |  |  | 13 | 95 | 10 | 0 | 6 | 11 | 135
Effort Estimates - Summary
Team | Total Hours | Estimated Cost (Only Onsite) | Estimated Cost (Onsite & Offshore)
Database | 29.7
ETL | 105.3
Tableau | 0
.NET | 0
QA Testing | 0
Business UAT | 40
Total | 135 | 0 | 0
Estimated days: | 17
Assumptions:
*These estimates are based on the existing requirements and does not account for any change requests.
*Any change requests will require re-estimation of efforts.
*These estimates include 40 hrs for UAT; if UAT extends beyond this time frame, then re-estimation may be required.
*The scheduling is based on the team's availability and bandwidth.
Complexity:
L - Low | <= 8 hrs
M - Medium | > 8 hrs and <= 16 hrs
H - High | > 16 hrs