## Cover Page
Project_Deliverables_Standards_Checklist Version V1.0 Date: Created by Valampuri NBCUniversal Internal
New Project | Operations & Technology (O&T)
Module | All Modules
Major Enhancements/ Adding new Subject areas | This document covers all the governance checkpoints carried for O&T project enhancements

## NBCU Standards
SL No | Best Practices | URL's
1 | Informatica | https://www.dropbox.com/sh/c1lmm5coxz7b90y/AADxuhKzVtp_xJeSAm5OEIo3a?dl=0
3 | Teradata | https://www.dropbox.com/sh/c1lmm5coxz7b90y/AADxuhKzVtp_xJeSAm5OEIo3a?dl=0
4 | Unix Scripts | https://www.dropbox.com/sh/u2gynekmn89rcgr/AAB9-zRCm0LSLDb5DEK9ejvEa?dl=0
5 | CTRL-M | https://www.dropbox.com/sh/o6hel37q9l8w2pb/AAAGkN4MVlSoZAl2ins_pe4Da?dl=0
6 | Data Model | https://www.dropbox.com/sh/8pn613n0jf5jb2h/AAAIia27CCOZJWu4Ps_7OC3Xa?dl=0

## Project Checklist
Project Name : O&T |  |  |  |  | RCO | Expense Reporting | GMO | Global Security | Data Security
Non Editable Fields |  |  | Editable fields
Phase | Task Details | Deliverables | Comments | Document Availability(Y/N) | Document Path | Document Path | Document Path | Document Path | Document Path | Project Comments
Project Grooming | Requirements Gathering | Business Requirements Document,Requirement traceability matrix |  | Y | https://nbcuni.sharepoint.com/sites/Corp_EDW/Shared%20Documents1/Projects/OTS%20Dashboard/01%20Rock%20Center%20Operations | https://nbcuni.sharepoint.com/sites/Corp_EDW/Shared%20Documents1/Projects/OTS%20Dashboard/02%20Expense%20Reporting\ | https://nbcuni.sharepoint.com/sites/Corp_EDW/Shared%20Documents1/Projects/OTS%20Dashboard/03%20Global%20Media%20Operations | https://nbcuni.sharepoint.com/sites/Corp_EDW/Shared%20Documents1/Projects/OTS%20Dashboard/04%20Global%20Security | https://nbcuni.sharepoint.com/sites/Corp_EDW/Shared%20Documents1/Projects/OTS%20Dashboard/05%20Data%20Security
| Estimation | Estimation Sheet |  | Y | https://nbcuni.sharepoint.com/sites/Corp_EDW/Shared%20Documents1/Projects/OTS%20Dashboard/01%20Rock%20Center%20Operations | https://nbcuni.sharepoint.com/sites/Corp_EDW/Shared%20Documents1/Projects/OTS%20Dashboard/02%20Expense%20Reporting\ | https://nbcuni.sharepoint.com/sites/Corp_EDW/Shared%20Documents1/Projects/OTS%20Dashboard/03%20Global%20Media%20Operations | https://nbcuni.sharepoint.com/sites/Corp_EDW/Shared%20Documents1/Projects/OTS%20Dashboard/04%20Global%20Security | https://nbcuni.sharepoint.com/sites/Corp_EDW/Shared%20Documents1/Projects/OTS%20Dashboard/05%20Data%20Security
| Kick Off Meeting | Project Charter & Milestones |  | N | NA | NA | NA | NA | NA
| Project Planning | Project Plan |  | N | https://nbcuni.sharepoint.com/sites/Corp_EDW/Shared%20Documents1/Projects/OTS%20Dashboard/01%20Rock%20Center%20Operations | https://nbcuni.sharepoint.com/sites/Corp_EDW/Shared%20Documents1/Projects/OTS%20Dashboard/02%20Expense%20Reporting\ | https://nbcuni.sharepoint.com/sites/Corp_EDW/Shared%20Documents1/Projects/OTS%20Dashboard/03%20Global%20Media%20Operations | https://nbcuni.sharepoint.com/sites/Corp_EDW/Shared%20Documents1/Projects/OTS%20Dashboard/04%20Global%20Security | https://nbcuni.sharepoint.com/sites/Corp_EDW/Shared%20Documents1/Projects/OTS%20Dashboard/05%20Data%20Security
Solutioning & Discovery | Data Analysis & profiling | Impact Analysis Document,Query Tracker |  | N | NA | NA | NA | NA | NA
| Data Modeling | Data model review checklist |  | Y | https://nbcuni.sharepoint.com/sites/Corp_EDW/Shared%20Documents1/Projects/OTS%20Dashboard/01%20Rock%20Center%20Operations | https://nbcuni.sharepoint.com/sites/Corp_EDW/Shared%20Documents1/Projects/OTS%20Dashboard/02%20Expense%20Reporting\ | https://nbcuni.sharepoint.com/sites/Corp_EDW/Shared%20Documents1/Projects/OTS%20Dashboard/03%20Global%20Media%20Operations | https://nbcuni.sharepoint.com/sites/Corp_EDW/Shared%20Documents1/Projects/OTS%20Dashboard/04%20Global%20Security | https://nbcuni.sharepoint.com/sites/Corp_EDW/Shared%20Documents1/Projects/OTS%20Dashboard/05%20Data%20Security
| Architecture Design | High level Design Document |  | Y | https://nbcuni.sharepoint.com/sites/Corp_EDW/Shared%20Documents1/Projects/OTS%20Dashboard/01%20Rock%20Center%20Operations | https://nbcuni.sharepoint.com/sites/Corp_EDW/Shared%20Documents1/Projects/OTS%20Dashboard/02%20Expense%20Reporting\ | https://nbcuni.sharepoint.com/sites/Corp_EDW/Shared%20Documents1/Projects/OTS%20Dashboard/03%20Global%20Media%20Operations | https://nbcuni.sharepoint.com/sites/Corp_EDW/Shared%20Documents1/Projects/OTS%20Dashboard/04%20Global%20Security | https://nbcuni.sharepoint.com/sites/Corp_EDW/Shared%20Documents1/Projects/OTS%20Dashboard/05%20Data%20Security
| ETL Design | Low Level Design Document |  | Y | https://nbcuni.sharepoint.com/sites/Corp_EDW/Shared%20Documents1/Projects/OTS%20Dashboard/01%20Rock%20Center%20Operations | https://nbcuni.sharepoint.com/sites/Corp_EDW/Shared%20Documents1/Projects/OTS%20Dashboard/02%20Expense%20Reporting\ | https://nbcuni.sharepoint.com/sites/Corp_EDW/Shared%20Documents1/Projects/OTS%20Dashboard/03%20Global%20Media%20Operations | https://nbcuni.sharepoint.com/sites/Corp_EDW/Shared%20Documents1/Projects/OTS%20Dashboard/04%20Global%20Security | https://nbcuni.sharepoint.com/sites/Corp_EDW/Shared%20Documents1/Projects/OTS%20Dashboard/05%20Data%20Security
Development | Database Changes | DB scripts |  | N | NA | NA | NA | NA | NA
| ETL Mapping Changes | Code / ETL Mapping,ETL Development tracker,Query Tracker |  | Y | https://nbcuni.sharepoint.com/sites/Corp_EDW/Shared%20Documents1/Projects/OTS%20Dashboard/01%20Rock%20Center%20Operations | https://nbcuni.sharepoint.com/sites/Corp_EDW/Shared%20Documents1/Projects/OTS%20Dashboard/02%20Expense%20Reporting\ | https://nbcuni.sharepoint.com/sites/Corp_EDW/Shared%20Documents1/Projects/OTS%20Dashboard/03%20Global%20Media%20Operations | https://nbcuni.sharepoint.com/sites/Corp_EDW/Shared%20Documents1/Projects/OTS%20Dashboard/04%20Global%20Security | https://nbcuni.sharepoint.com/sites/Corp_EDW/Shared%20Documents1/Projects/OTS%20Dashboard/05%20Data%20Security
| Unix Script Changes | Shell Scripts |  | Y | https://nbcuni.sharepoint.com/sites/Corp_EDW/Shared%20Documents1/Projects/OTS%20Dashboard/01%20Rock%20Center%20Operations | https://nbcuni.sharepoint.com/sites/Corp_EDW/Shared%20Documents1/Projects/OTS%20Dashboard/02%20Expense%20Reporting\ | https://nbcuni.sharepoint.com/sites/Corp_EDW/Shared%20Documents1/Projects/OTS%20Dashboard/03%20Global%20Media%20Operations | https://nbcuni.sharepoint.com/sites/Corp_EDW/Shared%20Documents1/Projects/OTS%20Dashboard/04%20Global%20Security | https://nbcuni.sharepoint.com/sites/Corp_EDW/Shared%20Documents1/Projects/OTS%20Dashboard/05%20Data%20Security
| Unit Testing | Unit Test results, Defect Tracker |  | Y | https://nbcuni.sharepoint.com/sites/Corp_EDW/Shared%20Documents1/Projects/OTS%20Dashboard/01%20Rock%20Center%20Operations | https://nbcuni.sharepoint.com/sites/Corp_EDW/Shared%20Documents1/Projects/OTS%20Dashboard/02%20Expense%20Reporting\ | https://nbcuni.sharepoint.com/sites/Corp_EDW/Shared%20Documents1/Projects/OTS%20Dashboard/03%20Global%20Media%20Operations | https://nbcuni.sharepoint.com/sites/Corp_EDW/Shared%20Documents1/Projects/OTS%20Dashboard/04%20Global%20Security | https://nbcuni.sharepoint.com/sites/Corp_EDW/Shared%20Documents1/Projects/OTS%20Dashboard/05%20Data%20Security
QA | Migration & Test Environment Preparation |  |  | Y | NA | NA | NA | NA | NA
| Testing & Defect Fixing | QA test plan, QA Test Case results, Defect Tracker, Load Statistics |  | Y | https://nbcuni.sharepoint.com/sites/Corp_EDW/Shared%20Documents1/Projects/OTS%20Dashboard/01%20Rock%20Center%20Operations | https://nbcuni.sharepoint.com/sites/Corp_EDW/Shared%20Documents1/Projects/OTS%20Dashboard/02%20Expense%20Reporting\ | https://nbcuni.sharepoint.com/sites/Corp_EDW/Shared%20Documents1/Projects/OTS%20Dashboard/03%20Global%20Media%20Operations | https://nbcuni.sharepoint.com/sites/Corp_EDW/Shared%20Documents1/Projects/OTS%20Dashboard/04%20Global%20Security | https://nbcuni.sharepoint.com/sites/Corp_EDW/Shared%20Documents1/Projects/OTS%20Dashboard/05%20Data%20Security
| UAT testing and support | UAT test Case results, Defect Tracker |  | Y | https://nbcuni.sharepoint.com/sites/Corp_EDW/Shared%20Documents1/Projects/OTS%20Dashboard/01%20Rock%20Center%20Operations | https://nbcuni.sharepoint.com/sites/Corp_EDW/Shared%20Documents1/Projects/OTS%20Dashboard/02%20Expense%20Reporting\ | https://nbcuni.sharepoint.com/sites/Corp_EDW/Shared%20Documents1/Projects/OTS%20Dashboard/03%20Global%20Media%20Operations | https://nbcuni.sharepoint.com/sites/Corp_EDW/Shared%20Documents1/Projects/OTS%20Dashboard/04%20Global%20Security | https://nbcuni.sharepoint.com/sites/Corp_EDW/Shared%20Documents1/Projects/OTS%20Dashboard/05%20Data%20Security
Review & Release | Deployment | Deployment Document,Release/Change request |  | Y | https://nbcuni.sharepoint.com/sites/Corp_EDW/Shared%20Documents1/Projects/OTS%20Dashboard/01%20Rock%20Center%20Operations | https://nbcuni.sharepoint.com/sites/Corp_EDW/Shared%20Documents1/Projects/OTS%20Dashboard/02%20Expense%20Reporting\ | https://nbcuni.sharepoint.com/sites/Corp_EDW/Shared%20Documents1/Projects/OTS%20Dashboard/03%20Global%20Media%20Operations | https://nbcuni.sharepoint.com/sites/Corp_EDW/Shared%20Documents1/Projects/OTS%20Dashboard/04%20Global%20Security | https://nbcuni.sharepoint.com/sites/Corp_EDW/Shared%20Documents1/Projects/OTS%20Dashboard/05%20Data%20Security
| Post Production Support | Support Documentation,KT handover checklist |  | Y | https://nbcuni.sharepoint.com/sites/Corp_EDW/Shared%20Documents1/Projects/OTS%20Dashboard/07%20Technical%20Documentation/ETL/OT_Support_Run_Book_ETL_v8.docx?d=w0bed88d02bcd44efb659849471323539 | https://nbcuni.sharepoint.com/sites/Corp_EDW/Shared%20Documents1/Projects/OTS%20Dashboard/02%20Expense%20Reporting\ | https://nbcuni.sharepoint.com/sites/Corp_EDW/Shared%20Documents1/Projects/OTS%20Dashboard/03%20Global%20Media%20Operations | https://nbcuni.sharepoint.com/sites/Corp_EDW/Shared%20Documents1/Projects/OTS%20Dashboard/04%20Global%20Security | https://nbcuni.sharepoint.com/sites/Corp_EDW/Shared%20Documents1/Projects/OTS%20Dashboard/05%20Data%20Security
| Automation of Data loads | Control-m Job Document |  | Y | https://nbcuni.sharepoint.com/sites/Corp_EDW/Shared%20Documents1/Projects/OTS%20Dashboard/07%20Technical%20Documentation/ETL/OT_INVENTORY_CONTROL_M_JOBS.xlsx?d=wbb3b61869c444cac8739aea502664018 | https://nbcuni.sharepoint.com/sites/Corp_EDW/Shared%20Documents1/Projects/OTS%20Dashboard/02%20Expense%20Reporting\ | https://nbcuni.sharepoint.com/sites/Corp_EDW/Shared%20Documents1/Projects/OTS%20Dashboard/03%20Global%20Media%20Operations | https://nbcuni.sharepoint.com/sites/Corp_EDW/Shared%20Documents1/Projects/OTS%20Dashboard/04%20Global%20Security | https://nbcuni.sharepoint.com/sites/Corp_EDW/Shared%20Documents1/Projects/OTS%20Dashboard/05%20Data%20Security
| Release Communications | Communication template |  | Y | https://nbcuni.sharepoint.com/sites/Corp_EDW/Shared%20Documents1/Projects/OTS%20Dashboard/07%20Technical%20Documentation/ETL/OTS%20Support%20Run%20Book%20Reference | https://nbcuni.sharepoint.com/sites/Corp_EDW/Shared%20Documents1/Projects/OTS%20Dashboard/02%20Expense%20Reporting\ | https://nbcuni.sharepoint.com/sites/Corp_EDW/Shared%20Documents1/Projects/OTS%20Dashboard/03%20Global%20Media%20Operations | https://nbcuni.sharepoint.com/sites/Corp_EDW/Shared%20Documents1/Projects/OTS%20Dashboard/04%20Global%20Security | https://nbcuni.sharepoint.com/sites/Corp_EDW/Shared%20Documents1/Projects/OTS%20Dashboard/05%20Data%20Security

## Governance Track
Integration Governance
S.No | Deployment Date | CR # | Governance SR # | Enhancement # | Change Desc | Checkpoint 1 | Check point 2 | Check point 3 | Check point 4
1 | Jul 31-2018 | CHG0149420 | RITM1367817 |  | Vimbiz Source system - 3. NET Server Change | Completed | Completed | Completed | Completed
2 | Jul 31-2018 | CHG0152305 | RITM1367877 |  | Green Zone: Expense Reporting - PCard Source system changes | Completed | Completed | Completed | Completed | Check Point 1 | Business Requirement Document Impact Analysis Document Requirement Traceability Matrix High level Design document
3 | Aug 02-2018 | CHG0147405 | RITM1376577 |  | STORM Automation of yearly budget prod load | Completed | Completed | Completed | Completed
4 | Aug 06-2018 | CHG0154525 | RITM1378433 |  | Green Zone: Post Production - New networks change | Completed | Completed | Completed | Completed
5 | 2018-09-20 | CHG0157279 | RITM1401773 | ENHC0033598 | The objective is to integrate global security data into 3 new tables in O&T Dashboard environment. | Completed | Completed | Completed | Completed
6 | 2018-10-11 | CHG0161786 | RITM1466001 | ENHC0035454 | Early late tracker - Phase2 ETL changes | Completed | Completed | Completed | Completed
|  |  | RITM1655648 | ENHC0037085 | The objective is to integrate Storm attendance trackerinto to 3 new tables in O&T Dashboard environment. | Completed | Completed
[10 empty] | Check Point 2 | Low Level Design Document Unit Test Plan & Test Cases Code / Scripts/ SQL Queries Test Results Query Tracker
[10 empty] | Check Point 3 | Stage & UAT Testing Results Defect tracker UAT Sign off Deployment Document Control-m Document
[10 empty] | Check Point 4 | KT Hand Over CheckList/Post Prod Validation
Notes
Define Migration activity window (Monday, Wednesday & Friday)
Production migration window occurs Monday through Thursday (excluding company holidays). All Prod Change tasks are required to be submitted a minimum of a 48 working hours (excludes weekend and company recognized holidays) prior to the requested implementation date/time

## Checkpoint 1
SI No. | Checkpoint RITM# | Checkpoint for | Review Date | Review Comments | Project Team Comments | Status | Final Comments
1 | RITM1401773 | https://nbcuni.sharepoint.com/sites/Corp_EDW/Shared%20Documents1/Forms/AllItems.aspx?RootFolder=%2Fsites%2FCorp_EDW%2FShared%20Documents1%2FProjects%2FOTS%20Dashboard%2F04%20Global%20Security%2F01%20Global%20Security%2FETL%2F02%20Design&FolderCTID=0x012000B69B8075BB074F4590AAA98395FA936B&View=%7B8D031AF4-0907-4A0B-8B38-410FE7541157%7D | Aug-24-2018 | Reviewed requirements. Sharepoint links to be updated | Updated the sharepoint links | Closed
2 | RITM1401773 | https://nbcuni.sharepoint.com/sites/Corp_EDW/Shared%20Documents1/Forms/AllItems.aspx?RootFolder=%2Fsites%2FCorp_EDW%2FShared%20Documents1%2FProjects%2FOTS%20Dashboard%2F04%20Global%20Security%2F01%20Global%20Security%2FETL%2F02%20Design&FolderCTID=0x012000B69B8075BB074F4590AAA98395FA936B&View=%7B8D031AF4-0907-4A0B-8B38-410FE7541157%7D | Aug-24-2018 | Reviewed HLD |  | Closed
3 | RITM1401773 | https://nbcuni.sharepoint.com/sites/Corp_EDW/Shared%20Documents1/Forms/AllItems.aspx?RootFolder=%2Fsites%2FCorp_EDW%2FShared%20Documents1%2FProjects%2FOTS%20Dashboard%2F04%20Global%20Security%2F01%20Global%20Security%2FETL%2F02%20Design&FolderCTID=0x012000B69B8075BB074F4590AAA98395FA936B&View=%7B8D031AF4-0907-4A0B-8B38-410FE7541157%7D | Aug-24-2018 | No impact to existing module , since its new module |  | Closed
4 | RITM1466001 | https://nbcuni.sharepoint.com/sites/Corp_EDW/Shared%20Documents1/Forms/AllItems.aspx?RootFolder=%2Fsites%2FCorp_EDW%2FShared%20Documents1%2FProjects%2FOTS%20Dashboard%2F03%20Global%20Media%20Operations%2FEarly%20Late%20Tracker&View=%7B8D031AF4-0907-4A0B-8B38-410FE7541157%7D | Oct-15-2018 | Requirement Traceability Matrix |  | Closed
5 | RITM1466001 | https://nbcuni.sharepoint.com/sites/Corp_EDW/Shared%20Documents1/Forms/AllItems.aspx?RootFolder=%2Fsites%2FCorp_EDW%2FShared%20Documents1%2FProjects%2FOTS%20Dashboard%2F03%20Global%20Media%20Operations%2FEarly%20Late%20Tracker%2FETL%2F02%20Design%2FETL&FolderCTID=0x012000B69B8075BB074F4590AAA98395FA936B&View=%7B8D031AF4-0907-4A0B-8B38-410FE7541157%7D&InitialTabId=Ribbon%2ERead&VisibilityContext=WSSTabPersistence | Oct-15-2018 | High level Design document |  | Closed
6 | RITM1655648 | https://nbcuni.sharepoint.com/sites/Corp_EDW/Shared%20Documents1/Forms/AllItems.aspx?FolderCTID=0x012000B69B8075BB074F4590AAA98395FA936B&id=%2Fsites%2FCorp_EDW%2FShared%20Documents1%2FProjects%2FOTS%20Dashboard%2FProduction%2F01%20Rock%20Center%20Operations%2FSTORM_NEW%2FETL%2F01%20Requirements | Mar-11-2019 | Reviewed requirements. Sharepoint links to be updated |  | Closed
7 | RITM1655648 | https://nbcuni.sharepoint.com/sites/Corp_EDW/Shared%20Documents1/Forms/AllItems.aspx?FolderCTID=0x012000B69B8075BB074F4590AAA98395FA936B&id=%2Fsites%2FCorp_EDW%2FShared%20Documents1%2FProjects%2FOTS%20Dashboard%2FProduction%2F01%20Rock%20Center%20Operations%2FSTORM_NEW%2FETL%2F02%20Design | Mar-11-2019 | HLD Document |  | Closed
Note on C1: Project/Enhancement Requirement

## Checkpoint 2
SI No. | Checkpoint RITM# | Checkpoint for | Review Date | Review Comments | Project Team Comments | Status | Final Comments
1 | RITM1401773 | https://nbcuni.sharepoint.com/sites/Corp_EDW/Shared%20Documents1/Forms/AllItems.aspx?RootFolder=%2Fsites%2FCorp_EDW%2FShared%20Documents1%2FProjects%2FOTS%20Dashboard%2F04%20Global%20Security%2F01%20Global%20Security%2FETL%2F02%20Design&FolderCTID=0x012000B69B8075BB074F4590AAA98395FA936B&View=%7B8D031AF4-0907-4A0B-8B38-410FE7541157%7D | Aug-24-2018 | Sharepoint links to be updated | Updated the sharepoint links | Closed
2 | RITM1401773 | https://nbcuni.sharepoint.com/sites/Corp_EDW/Shared%20Documents1/Forms/AllItems.aspx?RootFolder=%2Fsites%2FCorp_EDW%2FShared%20Documents1%2FProjects%2FOTS%20Dashboard%2F04%20Global%20Security%2F01%20Global%20Security%2FETL%2F07%20Project%20Support&FolderCTID=0x012000B69B8075BB074F4590AAA98395FA936B&View=%7B8D031AF4-0907-4A0B-8B38-410FE7541157%7D | Aug-24-2018 | SOP document looks good |  | Closed
3 | RITM1401773 | https://nbcuni.sharepoint.com/sites/Corp_EDW/Shared%20Documents1/Forms/AllItems.aspx?RootFolder=%2Fsites%2FCorp_EDW%2FShared%20Documents1%2FProjects%2FOTS%20Dashboard%2F04%20Global%20Security%2F01%20Global%20Security%2FETL%2F04%20QA&FolderCTID=0x012000B69B8075BB074F4590AAA98395FA936B&View=%7B8D031AF4-0907-4A0B-8B38-410FE7541157%7D | Aug-24-2018 | Unit test document |  | Closed
| RITM1466001 | https://nbcuni.sharepoint.com/sites/Corp_EDW/Shared%20Documents1/Forms/AllItems.aspx?RootFolder=%2Fsites%2FCorp_EDW%2FShared%20Documents1%2FProjects%2FOTS%20Dashboard%2F03%20Global%20Media%20Operations%2FEarly%20Late%20Tracker%2FETL%2F02%20Design%2FETL&FolderCTID=0x012000B69B8075BB074F4590AAA98395FA936B&View=%7B8D031AF4-0907-4A0B-8B38-410FE7541157%7D&InitialTabId=Ribbon%2ERead&VisibilityContext=WSSTabPersistence | Oct-15-2018 | LLD Document |  | Closed
| RITM1466001 | https://nbcuni.sharepoint.com/sites/Corp_EDW/Shared%20Documents1/Forms/AllItems.aspx?RootFolder=%2Fsites%2FCorp_EDW%2FShared%20Documents1%2FProjects%2FOTS%20Dashboard%2F03%20Global%20Media%20Operations%2FEarly%20Late%20Tracker%2FETL%2F04%20QA%2FTestCases&FolderCTID=0x012000B69B8075BB074F4590AAA98395FA936B&View=%7B8D031AF4-0907-4A0B-8B38-410FE7541157%7D | Oct-15-2018 | Test Case and result Document |  | Closed
| RITM1655648 | https://nbcuni.sharepoint.com/sites/Corp_EDW/Shared%20Documents1/Forms/AllItems.aspx?FolderCTID=0x012000B69B8075BB074F4590AAA98395FA936B&id=%2Fsites%2FCorp_EDW%2FShared%20Documents1%2FProjects%2FOTS%20Dashboard%2FProduction%2F01%20Rock%20Center%20Operations%2FSTORM_NEW%2FETL%2F02%20Design | Mar-11-2019 | LLD Document |  | Closed
| RITM1655648 | https://nbcuni.sharepoint.com/sites/Corp_EDW/Shared%20Documents1/Forms/AllItems.aspx?FolderCTID=0x012000B69B8075BB074F4590AAA98395FA936B&id=%2Fsites%2FCorp_EDW%2FShared%20Documents1%2FProjects%2FOTS%20Dashboard%2FProduction%2F01%20Rock%20Center%20Operations%2FSTORM_NEW%2FETL%2F04%20QA | Mar-11-2019 | Test Case and result Document |  | Closed
Note on C1: Project/Enhancement Requirement

## Checkpoint 3
SI No. | Checkpoint RITM# | Checkpoint for | Review Date | Review Comments | Project Team Comments | Status | Final Comments
1 | RITM1401773 | https://nbcuni.sharepoint.com/sites/Corp_EDW/Shared%20Documents1/Forms/AllItems.aspx?RootFolder=%2Fsites%2FCorp_EDW%2FShared%20Documents1%2FProjects%2FOTS%20Dashboard%2F04%20Global%20Security%2F01%20Global%20Security%2FETL%2F06%20Production%20Deployment&FolderCTID=0x012000B69B8075BB074F4590AAA98395FA936B&View=%7B8D031AF4-0907-4A0B-8B38-410FE7541157%7D | SEP-28-2018 | Got Signoff from Ryan | Job Signoff from Ryan | Closed
2 | RITM1401773 | https://nbcuni.sharepoint.com/sites/Corp_EDW/Shared%20Documents1/Forms/AllItems.aspx?RootFolder=%2Fsites%2FCorp_EDW%2FShared%20Documents1%2FProjects%2FOTS%20Dashboard%2F04%20Global%20Security%2F01%20Global%20Security%2FETL%2F06%20Production%20Deployment&FolderCTID=0x012000B69B8075BB074F4590AAA98395FA936B&View=%7B8D031AF4-0907-4A0B-8B38-410FE7541157%7D | SEP-28-2018 | Control M Job is scheduled as per plan | Control M team scheduled job | Closed
3 | RITM1401773 | https://nbcuni.sharepoint.com/sites/Corp_EDW/Shared%20Documents1/Forms/AllItems.aspx?RootFolder=%2Fsites%2FCorp_EDW%2FShared%20Documents1%2FProjects%2FOTS%20Dashboard%2F04%20Global%20Security%2F01%20Global%20Security%2FETL%2F06%20Production%20Deployment&FolderCTID=0x012000B69B8075BB074F4590AAA98395FA936B&View=%7B8D031AF4-0907-4A0B-8B38-410FE7541157%7D | SEP-28-2018 | Code in PROD looks good | Deployed the code to PROD | Closed
4 | RITM1466001 | https://nbcuni.sharepoint.com/sites/Corp_EDW/Shared%20Documents1/Forms/AllItems.aspx?RootFolder=%2Fsites%2FCorp_EDW%2FShared%20Documents1%2FProjects%2FOTS%20Dashboard%2F03%20Global%20Media%20Operations%2FEarly%20Late%20Tracker%2FETL%2F06%20Production%20Deployment&FolderCTID=0x012000B69B8075BB074F4590AAA98395FA936B&View=%7B8D031AF4-0907-4A0B-8B38-410FE7541157%7D | OCT-12-2018 | Code in PROD looks good | Deployed the code to PROD
5 | RITM1466001 | https://nbcuni.sharepoint.com/sites/Corp_EDW/Shared%20Documents1/Forms/AllItems.aspx?RootFolder=%2Fsites%2FCorp_EDW%2FShared%20Documents1%2FProjects%2FOTS%20Dashboard%2F03%20Global%20Media%20Operations%2FEarly%20Late%20Tracker%2FETL%2F07%20Project%20Support&FolderCTID=0x012000B69B8075BB074F4590AAA98395FA936B&View=%7B8D031AF4-0907-4A0B-8B38-410FE7541157%7D | OCT-12-2018 |  | Control M team scheduled job
6 | RITM1466001 | https://nbcuni.sharepoint.com/sites/Corp_EDW/Shared%20Documents1/Forms/AllItems.aspx?RootFolder=%2Fsites%2FCorp_EDW%2FShared%20Documents1%2FProjects%2FOTS%20Dashboard%2F04%20Global%20Security%2F01%20Global%20Security%2FETL%2F04%20QA&FolderCTID=0x012000B69B8075BB074F4590AAA98395FA936B&View=%7B8D031AF4-0907-4A0B-8B38-410FE7541157%7D | OCT-12-2018 |  | STAGE Test case Document
7 | RITM1655648 | https://nbcuni.sharepoint.com/sites/Corp_EDW/Shared%20Documents1/Forms/AllItems.aspx?FolderCTID=0x012000B69B8075BB074F4590AAA98395FA936B&id=%2Fsites%2FCorp_EDW%2FShared%20Documents1%2FProjects%2FOTS%20Dashboard%2FProduction%2F01%20Rock%20Center%20Operations%2FSTORM_NEW%2FETL%2F06%20Production%20Deployment | Mar-11-2019 |  | Production Deployment Document
8 | RITM1655648 | https://nbcuni.sharepoint.com/sites/Corp_EDW/Shared%20Documents1/Forms/AllItems.aspx?id=%2Fsites%2FCorp_EDW%2FShared%20Documents1%2FProjects%2FOTS%20Dashboard%2FProduction%2F10%20Technical%20Documentation%2FETL | Mar-11-2019 |  | Inventory Document
9 | RITM1655648 | https://nbcuni.sharepoint.com/sites/Corp_EDW/Shared%20Documents1/Forms/AllItems.aspx?FolderCTID=0x012000B69B8075BB074F4590AAA98395FA936B&id=%2Fsites%2FCorp_EDW%2FShared%20Documents1%2FProjects%2FOTS%20Dashboard%2FProduction%2F01%20Rock%20Center%20Operations%2FSTORM_NEW%2FETL%2F07%20Project%20Support | Mar-11-2019 |  | Control M job document
Note on C1: Project/Enhancement Requirement

## Checkpoint 4
SI No. | Checkpoint RITM# | CR# | Checkpoint for | Review Date | Review Comments | Project Team Comments | Status | Final Comments
1 | RITM1401773 | CHG0157279 | https://nbcuni.sharepoint.com/sites/Corp_EDW/Shared%20Documents1/Forms/AllItems.aspx?RootFolder=%2Fsites%2FCorp_EDW%2FShared%20Documents1%2FProjects%2FOTS%20Dashboard%2F04%20Global%20Security%2F01%20Global%20Security%2FETL%2F07%20Project%20Support&FolderCTID=0x012000B69B8075BB074F4590AAA98395FA936B&View=%7B8D031AF4-0907-4A0B-8B38-410FE7541157%7D | SEP-27-2018 |  | Gave KT to Support team | Closed
2 | RITM1466001 |  | https://nbcuni.sharepoint.com/sites/Corp_EDW/Shared%20Documents1/Forms/AllItems.aspx?RootFolder=%2Fsites%2FCorp_EDW%2FShared%20Documents1%2FProjects%2FOTS%20Dashboard%2F03%20Global%20Media%20Operations%2FEarly%20Late%20Tracker%2FETL%2F07%20Project%20Support&FolderCTID=0x012000B69B8075BB074F4590AAA98395FA936B&View=%7B8D031AF4-0907-4A0B-8B38-410FE7541157%7D | OCT-16-2018 |  | Gave KT to Support team
RITM1655648
Note on D1: Project/Enhancement Requirement