## Dashboard
KT Plan
Stage | # Open | # In Progress | # Closed | % Completed
KT Plan | 14 | 0 | 0 | 0%
Access | 0 | 0 | 9 | 100%
Inventory |  |  |  | 100%
Archictecture | 0 | 0 | 0 | 100%
Server Credentials |  |  |  | 100%
Contacts | 0 | 0 | 3 | 100%
Overall | 14 | 0 | 12 | 83.33%
[5 empty] | Count of Status | Column Labels
[5 empty] | Row Labels | All | DB | Drupal | Web | Grand Total | Queue | % Completion
[5 empty] | Closed | 10 | 10 | 3 | 64 | 87 | Web | 98.67%
[5 empty] | In Progress |  |  |  | 1 | 1 | Drupal | 100%
[5 empty] | (blank) | [5 empty] | DB | 100%
[5 empty] | Grand Total | 10 | 10 | 3 | 65 | 88 | Overall | 97.73%

## 1. KT Plan
`
Stream | Tasks | Discussion Sessions | Checklist | Assigned | Start Date | End Date | Status
All | Knowledge Transition ( From Raj)
Storm Attendance Tracker | Source data , INFA Mapping and Workflow |  |  | Preetha | 2019-06-11 | 2019-06-11 | Open
| scripts , parameter files,EACS and other challenges |  |  | Preetha | 2019-06-12 | 2019-06-12 | Open
Studio Post | Source data , INFA Mapping and Workflow |  |  | Preetha | 2019-06-13 | 2019-06-13 | Open
| scripts , parameter files,EACS and other challenges |  |  | Preetha | 2019-06-17 | 2019-06-17 | Open
Absorb | Source data , INFA Mapping and Workflow |  |  | Preetha | 2019-06-18 | 2019-06-18 | Open
| scripts , parameter files,EACS and other challenges |  |  | Preetha | 2019-06-19 | 2019-06-19 | Open
Global Security | Source data , INFA Mapping and Workflow |  |  | Preetha | 2019-06-20 | 2019-06-20 | Open
| scripts , parameter files,EACS and other challenges |  |  | Preetha | 2019-06-20 | 2019-06-20 | Open
DSR | DSR |  |  | Preetha | 2019-06-21 | 2019-06-21 | Open
| Updating efforts |  |  | Preetha | 2019-06-21 | 2019-06-21 | Open
| Updating DSR main page |  |  | Preetha | 2019-06-21 | 2019-06-21 | Open
GMO MED,EC and INTL | Source data , INFA Mapping and Workflow |  |  | Preetha | 2019-06-24 | 2019-06-24 | Open
| scripts , parameter files,EACS and other challenges |  |  | Preetha | 2019-06-25 | 2019-06-25 | Open
LYFT CAR SERVICES | Source data , INFA Mapping and Workflow |  |  | Preetha | 2019-06-26 | 2019-06-26 | Open
| scripts , parameter files,EACS and other challenges |  |  | Preetha | 2019-06-26 | 2019-06-26 | Open
Code Deployment | Deployment Document preparation for Prod movement |  |  | Preetha | 2019-06-27 | 2019-06-27 | Open
| stage deployment & Testing process |  |  | Preetha | 2019-06-27 | 2019-06-27 | Open
| Entire Process flow |  |  | Preetha | 2019-06-27 | 2019-06-27 | Open
WSR | WSR |  |  | Preetha | 2019-06-28 | 2019-06-28 | Open
| Preparing Demand Planning Document |  |  | Preetha | 2019-06-28 | 2019-06-28 | Open
| Preparing Project Management and WSR PPT |  |  | Preetha | 2019-06-28 | 2019-06-28 | Open
| Preparing data for graphs,Weekly efforts,Ticket counts |  |  | Preetha | 2019-06-28 | 2019-06-28 | Open
Documentation & MISC | Review of all the documents related to OT Deveoplment and other OT related activites |  |  | Preetha | 2019-07-01 | 2019-07-01 | Open
All | Knowledge Transition (From Aswin)
| Understanding project and going through documents |  |  | Preetha |  |  | Open
All | Shadow Support From Raj
| Shadow Support |  |  | Preetha | 2019-07-02 | 2019-07-03 | Open
| Reverse KT |  |  | Preetha | 2019-07-03 | 2019-07-03 | Open
All | Shadow Support From Aswin
| Shadow Support |  |  | Preetha |  |  | Open
| Reverse KT |  |  | Preetha |  |  | Open
All | Primary Support
| Single point of Contact for O&T projects and Support |  |  | Paul Naveen | Feb-01-2019 |  | Open
[6 empty] | Completion % | 0%

## 2.Access Required
Access and Approvals
Name | Technology | SSO | Status | Service Request
Informatica Dev | Informatica | 206453272 | Closed
Informatica Stage | Informatica | 206453272 | Closed
Informatica Prod | Informatica | 206453272 | Closed
Teradata Dev | Teradata | 206453272 | Closed
Teradata Stage | Teradata | 206453272 | Closed
Teradata Prod | Teradata | 206453272 | Closed
Informatica batch Server Dev | Informatica | 206453272 | Closed
Informatica batch Server Stage | Informatica | 206453272 | Closed
Informatica batch Server Prod | Informatica | 206453272 | Closed
Share Point Access | Share Point Access | 206453272 | Closed
OTS mailbox access | Mailbox | 206453272 | Closed
Adding Paul in all DL's | Communication/Mails | 206453272 | Closed

## 3.Inventory
Refer the below mentioned onedrive link
https://nbcuni.sharepoint.com/:x:/s/Corp_EDW/EYZhO7tEnKxMhzmupQJmQBgBD4O-Fp2PVuO1_ETtgdxc2Q?e=cVvzqs

## 4. Architecture
Refer the below mentioned onedrive link
https://nbcuni.sharepoint.com/:w:/s/Corp_EDW/EfrwMwh6InxOvrQBI4NgkRcBnSNGtp42qpc3xZJTl_HX9g?e=dmds4X

## 5.Server Credentials
Server Credentials
Application Name | Application Url | Username (for all env) | Monitoring Server (ICINGA) | Password
ETL Load id dev | TDDEV | OTSDW_LOAD_01
ETL Load id stage | TDSTAGE | OTSDW_LOAD_01
ETL Load id Prod | TDPRODLA | OTSDW_LOAD_01
TheCenter portal user id | TDPRODLA | OTSDW_BI_01
batch server | Dev | otsxfr
batch server | Stage | otsxfr
batch server | Prod | otsxfr
batch server | Dev | otsbat
batch server | Stage | otsbat
batch server | Prod | otsbat
Thecenterstage Node 1 | \\USUSHWSWS221LA\OTS
Thecenterstage Node 2 | \\USUSHWSWS221LB\OTS
ThecenterProd Node 1 | \\USUSHWSWP222LA\OTS
ThecenterProd Node 2 | \\USUSHWSWP222LB\OTS
Vimbiz Dev |  |  | Hostname: denvimbizdb.tfayd.com IP Address: 100.125.236.24 Username: execvalidation Password:
Vimbiz Prod |  |  | Server Name: 3.3.84.222, 4070 Username: execdashboard Password:
GMO Post Production - Dev |  | schedwin | Server: AOADBWS00032\S0134ES01, 4070 Database: SCHEDWIN_NOC_STG
GMO Post Production - Stage |  | schednocread | AOADBWQ00014\Q0134ES01, 4070 (SCHEDWIN_NOC_QA)
GMO Post Production - Prod |  | schednocread | Database Server / Listener : LSNRSOPEP01, 4070  Currently connected to AOADBWP00125\P0134ES02, 4070 primary database Database Name : SCHEDWIN_NOC_PROD
GMO Mediator |  |  | 1. Login to server : 100.115.114.21 2. Enter login id/Pwd: 206430938/ 3. Open DB Visualizer connect to Mediator connection 4. Database username\pwd = med_readonly\ TNS Entry: jdbc:oracle:thin:@(DESCRIPTION=(ADDRESS=(PROTOCOL=TCP)(HOST=mtpdboda503-scan.mts.inbcu.com)(PORT=1521))(CONNECT_DATA=(SERVER=DEDICATED)(SERVICE_NAME=MTPDB3A)))
\\USHAPWP00240\iscoeshare\OTS_PROD
\\USHAPWP00240\iscoeshare\OTS_QA
ETL Service Account |  | 206487762
Storage folder location for uploading User Guide | \\usushnvnp087\app_ots_dashboard\

## 6.Contacts
Name | Capgemini / NBCU | NBCUniversal Email id | Personal Contact | Status
Paul Naveen | Capgemini | Paulnaveen.selvakumar@nbcuni.com | +1 646 469 2039 | Closed
Rajasekhar | Capgemini | Rajasekhar.Boppasamudram@nbcuni.com | +91-9176962211 | Closed
Aswin | Capgemini | Aswin.Madhavan@nbcuni.com | 956-615-8618 | Closed
|  |  | Completion % | 100%
Contact list is present in Support Run Book too

## Documentation
Sharepoint Link
https://nbcuni.sharepoint.com/:f:/s/Corp_EDW/EqxtREdTpFhHuc5BlRGMbUoBGZ38e3aX9H2emm88ODLcHQ?e=lKaMUR
SOP
https://nbcuni.sharepoint.com/:f:/s/Corp_EDW/EiUhAfPJuapKotwSzV6h63gBb-xHH2j_2G9ReyR7JJUK9w?e=Yl85uJ
Scheduled Job Details
https://nbcuni.sharepoint.com/:x:/s/Corp_EDW/EQx549iWMMZDo4z5jMwlDaEBwheFzg37sHibWnzEbGeo_A?e=inry1i