## Index
| Application Name | O&T Dashboard
| SOP Scope | TERADATA DEV Testing
| Deployment Start Date & Time (EST) | 05/10/2019 06:00PM EST
| Deployment End Date & Time (EST) | 05/12/2019 05:00PM EST
Application Testing Support for Teradata Upgrade - SOP
# | Index
1 | Change Request & Contact Info
2 | TERADATA Test Plan

## Change Request & Contact Info (hidden)
Deployment Change Request
Change Request # | CTASK # | Team | Description | CTASK Owner
CHG0124285 | NA | BTG Tableau / ETL | Environment Testing & Verification | BTG Tableau / ETL Teams
Change Management Bridge (BO) Details
Conference Bridge Number (Direct Dial) | 212-413-5247
Conference Bridge Number (Toll Free) | 877-622-4588
BO | 30
Teams
Name | SSO | Team | Work Phone | Mobile Phone | Availability
BTG Tableau
Paul Thomas | 206088647 | BTG Tableau | 212-887-5932 | 917-270-7908 | Mandatory
Vaikunth Gopalakrishnan | 502155736 | BTG Tableau | 212-887-5940 | 201-207-7468 | Mandatory
Business
Tynelle Spooner | 204035224 | Business | 212-664-6108 | 201-248-4408 | Mandatory
Tableau & ETL Supporting
Rituraj Kumar | 206475458 | Tableau Developer (Onsite) | 212-887-0607 | 732-491-6072 | Mandatory
Arshadh Ariff | 206495668 | Tableau Developer (Onsite) | 212-413-5726 | 551-225-4534 | Mandatory
Valampuri Nakiran | 206478889 | ETL Developer (Onsite) | 201-735-6607 | 201-554-9159 | Mandatory
Muruganandham Premkumar | 206441978 | Front End Developer (Offshore) | 044-47444444*2874 | 919962969534 | Mandatory
Infrastructure
Sardar Ahmed | 206451841 | Teradata Team | 818-777-4231 | 818-371-1192 | Mandatory
Steven Koller | 206060143 | Teradata Team | 818-777-6485 | 818-632-2134 | Mandatory
Mike Burgwald | 206457108 | Teradata Team | 818-777-6810 | 818-232-1233 | Mandatory
CorpSys
Revanth Nemdhari | 206529966 | CorpSys Tableau | 212-664-6093 | 704-705-0775 | Mandatory
Mike Haladjian | 206047644 | CorpSys Tableau | 818-777-3550 | 818-383-2523 | Mandatory
Escalation List
Level | Team Name | Lead Location | Lead Name | Mobile Phone | Email
1 | BTG Tableau/ETL | Onsite | Paul Thomas | 917-270-7908 | Paul.Thomas@nbcuni.com
2 | Teradata Team | Onsite | Sardar Ahmed | 818-371-1192 | Sardar.Ahmed@nbcuni.com

## Environment Details (hidden)
Old Configuration |  |  |  | New Configuration
Teradata Database |  |  |  | Teradata Database
Environment | DB Instance Name | IP Address |  | Environment | DB Instance Name | IP Address
Production | TDPRODLA.tfayd.com | 100.114.110.212 |  | Production | TDPRODLA.tfayd.com | Multiple - see below
|  | Tableau Servers- No Change |  |  |  | Teradata Production Servers
|  | Environment | Hostname / Function | IP Address |  | USHDBLP00202 100.114.220.136
|  | Production | USHAPWP00788 / Primary | 100.114.111.8 |  | USHDBLP00203 100.114.220.137
|  |  | USHAPWP00789 / Worker | 100.114.111.9 |  | USHDBLP00204 100.114.220.138
|  |  | USHAPWP00790 / Worker | 100.114.111.10 |  | USHDBLP00205 100.114.220.139
|  |  | USHAPWP00791 / Worker | 100.114.111.11 |  | USHDBLP00206 100.114.220.140
|  |  | USHAPWP00820 / Worker | 100.114.111.22 |  | USHDBLP00207 100.114.220.141
USHDBLP00208 100.114.220.142
|  | Web Servers (TheCenter) - No Change |  |  |  | USHDBLP00209 100.114.220.143
|  | Environment | Hostname | IP Address |  | USHDBLP00210 100.114.220.144
|  | Production | USUSHWSWP222LA | 3.156.19.229 |  | USHDBLP00211 100.114.220.145
|  |  | USUSHWSWP222LB | 3.156.19.230 |  | USHDBLP00212 100.114.220.146
USHDBLP00213 100.114.220.147
|  | theCenter & Tableau URLs - No Change |  |  |  | USHDBLP00214 100.114.220.148
|  | Environment | Function | URL |  | USHDBLP00215 100.114.220.149
|  | Production | CorpSys Tableau | http://corpsystableauprod.inbcu.com/ |  | USHDBLP00216 100.114.220.150
|  |  | theCenter Node 1 | http://thecenter1.inbcu.com/ |  | USHDBLP00217 100.114.220.151
|  |  | theCenter Node 2 | http://thecenter2.inbcu.com/ |  | USHDBLP00218 100.114.220.152
|  |  | theCenter VIP | http://thecenter.inbcu.com/ |  | USHDBLP00219 100.114.220.153
USHDBLP00220 100.114.220.154
USHDBLP00221 100.114.220.155
USHDBLP00222 100.114.220.156

## Teradata Migration Steps (hidden)
Deployment Steps
| OVERALL PROGRESS : 81.4% |  |  | 81.4
SNo | Task | Duration in Minutes | CTASK | Start Time | End Time | Task Owner [Team(s)] | Notes | Weightage | Status | Parallel Tasks
PRE-DEPLOYMENT STEPS
1 | New NBCU12 shut down and turned over to Teradata for final target system prep | 180 | NA | 1/4/18 7:00 PM | 1/4/18 10:00 PM | Teradata Team |  | 3.7 | Complete
2 | Put theCenter application into maintenance in M360 | 15 | NA | 2018-01-05 15:00 | 2018-01-05 15:15 | BTG Tableau |  | 3.7 | Complete
3 | Put ETL jobs on Hold in Control-M | 15 | NA | 2018-01-05 15:00 | 2018-01-05 15:15 | BTG ETL |  | 3.7 | Complete
4 | Take Tableau Inventory (count of Folders, Workbooks, Data Sources, Users, Groups) | 15 | NA | 2018-01-05 15:15 | 2018-01-05 15:30 | BTG Tableau |  | 3.7 | Complete
5 | ETL tables inventory (Record Count in NBCU6) & Load Stats (Last Run in NBCU6) | 45 | NA | 2018-01-05 15:15 | 2018-01-05 16:00 | BTG ETL |  | 3.7 | Complete
6 | Old NBCU6 migration Start Time/ System Shut Down | 210 | NA | 1/6/18 12:00 AM | 1/6/18 3:30 AM | Teradata Team |  | 3.7 | Complete
7 | Old NBCU6 to new NBCU12 NPARC data copy begins | 720 | NA | 1/6/18 3:30 AM | 1/6/18 3:30 PM | Teradata Team |  | 3.7 | Complete
8 | New NBCU12 Object migration, statistics recollection & DBA system test complete | 990 | NA | 1/6/18 3:30 PM | 1/7/18 8:00 AM | Teradata Team |  | 3.7 | Complete
DEPLOYMENT STEPS
9 | Receive Notification from Teradata Team for application testing | 5 | NA | 2018-01-07 08:45 | 2018-01-07 08:50 | Teradata Team |  | 3.7 | Complete
10 | Get the recent Tableau Inventory count and compare with inventory taken earlier | 30 | NA | 2018-01-07 08:50 | 2018-01-07 09:20 | BTG Tableau |  | 3.7 | Complete
11 | Get the recent Record count and compare with ETL tables Inventory taken earlier | 30 | NA | 2018-01-07 08:50 | 2018-01-07 09:20 | BTG ETL |  | 3.7 | Complete
12 | Perform Tableau Testing as per Tableau Test Plan | 60 | NA | 2018-01-07 09:20 | 2018-01-07 10:20 | BTG Tableau |  | 3.7 | Complete
13 | Perform ETL Testing as per ETL Test Plan | 60 | NA | 2018-01-07 09:20 | 2018-01-07 10:20 | BTG ETL |  | 3.7 | Complete
14 | Verify that theCenter is online and working fine http://thecenter1.inbcu.com/ http://thecenter2.inbcu.com/ http://thecenter.inbcu.com/ | 15 | NA | 2018-01-07 10:20 | 2018-01-07 10:35 | BTG Tableau / ETL |  | 3.7 | Complete
15 | BTG Tableau & ETL signoff | 5 | NA | 2018-01-07 10:35 | 2018-01-07 10:40 | BTG Tableau |  | 3.7 | Complete
16 | GO OR NO GO AFTER TABLEAU & ETL TESTING | 5 | NA | 2018-01-07 10:40 | 2018-01-07 10:45 | BTG Tableau |  | 3.7 | Complete
17 | Business Application Testing | 30 | NA | 2018-01-07 10:45 | 2018-01-07 11:15 | Business |  | 3.7 | Complete
18 | Business team signoff | 5 | NA | 2018-01-07 11:15 | 2018-01-07 11:20 | Business |  | 3.7 | Complete
19 | GO OR NO GO AFTER BUSINESS TESTING | 5 | NA | 2018-01-07 11:20 | 2018-01-07 11:25 | Business |  | 3.7 | Complete
20 | Go–No Go Decision from Teradata Team | 30 | NA | 2018-01-07 13:00 | 2018-01-07 13:30 | Teradata Team |  | 3.7 | Complete
21 | New TDPRODLA system released to stakeholders | 5 | NA | 2018-01-07 13:30 | 2018-01-07 13:35 | Teradata Team |  | 3.7 | Complete
22 | Send notifications to the users that O&TS Dashboard is back online | 5 | NA | 2018-01-07 13:35 | 2018-01-07 13:40 | BTG Tableau |  | 3.7 | Complete
Total Duration |  | 290
POST DEPLOYMENT STEPS
23 | Ensure CorpSys - Application and components are out of M360 maintenance. | 5 | NA | 2018-01-07 13:40 | 2018-01-07 13:45 | BTG Tableau | Ritu to remove at 10:40 EST | 3.7 | Complete
24 | Release ETL jobs in Control-m | 5 | NA | 2018-01-07 13:40 | 2018-01-07 13:45 | BTG ETL | Reset at 1:30 PM EST | 3.7 | Complete
25 | Monitor the daily & weekly ETL loads on 1/8/18 | 360 | NA | 2018-01-08 | 2018-01-08 06:00 | BTG ETL | Offshore team to perform | 3.7 | Complete
26 | Load Stats comparison(NBCU6 vs NBCU12) | 30 | NA | 2018-01-08 10:00 | 2018-01-08 10:30 | BTG ETL | Offshore team to perform | 3.7 | Complete
27 | Monitor the daily Tableau extract refreshes on 1/8/18 | 360 | NA | 2018-01-08 | 2018-01-08 06:00 | BTG Tableau |  | 3.7 | Not Started
In Progress
Complete
Not CorpSys - Applicable
Formulas:
End Time = [Start Time]+TIME(0,[Duration in Minutes],0)
Start Time = [End Time, row above]
Start Time = [Start Time, row above]

## TERADATA Test Plan
SNo | Test Case | Testing Steps | Test Data | Expected Results | Actual Results | Test Results | Screenshots and Notes
ID.1 | Connecting toTERADATA DEV environment | Try to connect to TERADATA TDDEV | Database : TDDEV SCHEMA : OTSDW_VM,GMODW_VM and STORM_VM | Should be able to connect to all the databases | Able to connect to all the databases | Pass | TC1
ID.2 | Viewing Data | Should see data in OTSDW_VM,GMODW_VM and STORM_VM | SCHEMA : OTSDW_VM,GMODW_VM and STORM_VM | Should see the data | We are able to see the data | Pass | TC2
ID.3 | Loading the Data into Teradata tables | Run ETL data load and capture test results | Run any OT workflow | Workflow should complete successfully | Workflow completed successfully | Pass | TC3

## TC1
OTS |  | GMO
STORM

## TC2
OTS
GMO
STORM

## TC3
OTS WORKFLOW